## Schedule of Values
Cashman Marine — Hypothetical Project
Schedule of Values · Total Contract: $32,000,000 · Period billed to date: ~32% · Retention rate: 10%
Columns G, H, I, J, K, L need formulas. Use AI to generate them, then test with known values before trusting the totals.
# | Division | Line Item Description | Total Contract Amount | Previously Billed | This Period | Total Billed (formula) | % Complete (formula) | Remaining (formula) | Retention 10% (formula) | Net Earned to Date (formula) | Status (formula)
1 | 01 — General Requirements | Mobilization | 1200000 | 1050000 | 150000
2 | 01 — General Requirements | Bonds & Insurance | 480000 | 480000 | 0
3 | 01 — General Requirements | Project Management (monthly) | 700000 | 180000 | 44000
4 | 01 — General Requirements | Field Office / Temporary Facilities | 320000 | 270000 | 50000
5 | 01 — General Requirements | Quality Control Program | 300000 | 75000 | 21000
6 | 02 — Existing Conditions | Demolition of existing structures | 1800000 | 1500000 | 210000
7 | 02 — Existing Conditions | Disposal & Hauling | 600000 | 380000 | 70000
8 | 03 — Concrete | Cast-in-place concrete (caps) | 2400000 | 180000 | 180000
9 | 03 — Concrete | Reinforcing steel | 880000 | 100000 | 93600
10 | 03 — Concrete | Formwork | 720000 | 100000 | 101600
11 | 05 — Metals | Sheet pile fabrication | 4200000 | 2400000 | 330000
12 | 05 — Metals | Sheet pile delivery to site | 480000 | 200000 | 88000
13 | 05 — Metals | Miscellaneous structural steel | 520000 | 40000 | 22400
14 | 31 — Earthwork | Dredging | 3600000 | 1050000 | 318000
15 | 31 — Earthwork | Backfill | 1400000 | 0 | 0
16 | 33 — Utilities | Stormwater management | 400000 | 0 | 0
17 | 35 — Marine Construction | Sheet pile installation | 5800000 | 400000 | 296000
18 | 35 — Marine Construction | Pile driving | 3200000 | 0 | 160000
19 | 35 — Marine Construction | Fender system installation | 1800000 | 0 | 0
20 | 35 — Marine Construction | Mooring hardware | 880000 | 0 | 0
21 | 35 — Marine Construction | Demobilization & site restoration | 320000 | 0 | 0
DIVISION SUBTOTALS
| 01 — General Requirements | (SUMIFS by division — formula needed)
| 02 — Existing Conditions | (SUMIFS by division — formula needed)
| 03 — Concrete | (SUMIFS by division — formula needed)
| 05 — Metals | (SUMIFS by division — formula needed)
| 31 — Earthwork | (SUMIFS by division — formula needed)
| 33 — Utilities | (SUMIFS by division — formula needed)
| 35 — Marine Construction | (SUMIFS by division — formula needed)
| PROJECT TOTAL | (SUM across all line items — formula needed)
Notes for the formula columns:
Total Billed (G) = Previously Billed (E) + This Period (F)
% Complete (H) = Total Billed (G) / Total Contract Amount (D)
Remaining (I) = Total Contract Amount (D) − Total Billed (G)
Retention 10% (J) = Total Billed (G) × 10%
Net Earned to Date (K) = Total Billed (G) − Retention (J)
Status (L) = COMPLETE ¦ NEAR COMPLETE (≥90%) ¦ IN PROGRESS (>0%) ¦ NOT STARTED (0%)
Division subtotals = SUMIFS by division (one row per division)
Project Total = SUM of each numeric column across all line items