## Change Orders
Sunflower Plains Boiler Install — PM Cost Tracker
Project: IPC-2025-184 · Client: Sunflower Plains Ag Processing, LLC · Maintained by: Karen Hayes
CO # | Date | Description | Status | Approved $ | Notes
CO-001 | 2025-11-04 | Owner-requested upgrade: package boiler from 1.0 to 1.2 MMBtu/hr to handle planned dryer #3 expansion | Approved | 240000 | Per Brad email 11/3
CO-002 | 2025-11-21 | Differing site conditions — 4 ft of unmarked rebar in slab where boiler pad goes | Approved | 78500 | Field-verified by Dale
CO-003 | 2025-12-09 | Add insulation upgrade (from 1.5" to 2" calcium silicate) on steam header per owner engineer review | Approved | 54000 | Linda Park request
CO-004 | 2026-01-14 | Re-route gas line — owner discovered abandoned ag chemical tank under planned route | Approved | 186000 | Required ESA review; 3-wk delay
CO-005 | 2026-01-28 | Owner request: tie-in DCS to MES system (was not in original scope) | Approved | 142000 | Wei flagged as out of scope
CO-006 | 2026-02-18 | Replace blowdown tank — supplier shipped wrong material grade (304SS instead of 316SS) | Pending | 96000 | Dispute with supplier; may be backcharge
CO-007 | 2026-03-09 | Crew overtime — owner requested accelerated schedule to recover from CO-004 delay | Approved | 220000 | Two-shift coverage 4 weeks
CO-008 | 2026-03-24 | Additional control valves on feedwater train — owner spec changed mid-fab | Approved | 88000 | Affected fab schedule
CO-009 | 2026-04-22 | Crane re-mob — high winds canceled first attempt, lost a full day plus rental | Approved | 34000 | Weather
CO-010 | 2026-05-12 | Punch list scope creep: owner added 17 items not in original closeout spec | Pending | 62000 | Negotiating

## Requisitions
Requisitions Submitted
Req # | Period | Submitted | Approved | Requested $ | Approved $ | Status / Notes
REQ-1 | Oct 2025 | 2025-11-05 | 2025-11-19 | 840000 | 840000 | Paid
REQ-2 | Nov 2025 | 2025-12-04 | 2025-12-22 | 1120000 | 1080000 | Paid (40k held — disputed mob)
REQ-3 | Dec 2025 | 2026-01-06 | 2026-01-23 | 1240000 | 1240000 | Paid
REQ-4 | Jan 2026 | 2026-02-05 | 2026-02-26 | 980000 | 910000 | Paid (70k disputed — CO-004 delay credit)
REQ-5 | Feb 2026 | 2026-03-04 | 2026-03-24 | 1440000 | 1440000 | Paid
REQ-6 | Mar 2026 | 2026-04-08 | 2026-04-29 | 1680000 | 1680000 | Paid
REQ-7 | Apr 2026 | 2026-05-06 | 2026-05-26 | 1320000 | 1280000 | Paid (40k held — punch list)
REQ-8 | May 2026 | 2026-06-09 | Pending | 890000 | 0 | In review — disputed CO-006 + CO-010

## Cost Summary
Cost Bucket Summary (PM rolling forecast)
Note: this was hand-edited by the PM each month; see emails for caveats. Numbers do not exactly tie to requisitions.
Cost Bucket | Original Budget | Forecast at Closeout | Variance
Direct Labor | 2400000 | 2980000 | 580000
Major Equipment (Boiler skid) | 1900000 | 1920000 | 20000
Subcontractors — Mechanical | 1650000 | 1910000 | 260000
Subcontractors — Electrical | 780000 | 840000 | 60000
Materials — Piping/Fittings | 520000 | 615000 | 95000
Materials — Insulation | 180000 | 235000 | 55000
Crane / Rigging | 240000 | 305000 | 65000
Permits / Fees | 60000 | 72000 | 12000
PM / Engineering / Closeout | 370000 | 430000 | 60000
Contingency | 300000 | 558000 | 258000
TOTAL | 8400000 | 9865000 | 1465000