## Project Portfolio
Cashman Companies — Hypothetical Project Portfolio (training data)
32 hypothetical projects across Dredging, Pile Driving, IPC Lydon, and Preload Cryogenics. All names, regions, and figures are made up for AI-training use only. Ask AI which project type tends to go over budget and why.
Project Name | Project Type | Region | Contract Value | Final Cost | Cost Variance | Planned Duration (months) | Actual Duration (months) | Schedule Variance (months) | # Change Orders | Change Order Total | Project Manager | Status
Boston Inner Harbor Channel Maint | Dredging | Boston, MA | 4200000 | 4120000 | -80000 | 4 | 4 | 0 | 1 | 80000 | Bobby M. | Complete
New Bedford Harbor Deepening | Dredging | New Bedford, MA | 12400000 | 13900000 | 1500000 | 11 | 13 | 2 | 4 | 920000 | Bobby M. | Complete
Providence River Channel Restoration | Dredging | Providence, RI | 6800000 | 6650000 | -150000 | 6 | 6 | 0 | 2 | 140000 | Sarah K. | Complete
Portland Berth 7 Maintenance | Dredging | Portland, ME | 3100000 | 3090000 | -10000 | 3 | 3 | 0 | 0 | 0 | Bobby M. | Complete
Long Island Sound Disposal Site | Dredging | Long Island, NY | 9600000 | 11200000 | 1600000 | 8 | 11 | 3 | 6 | 1350000 | Sarah K. | Complete
Chesapeake Approach Channel | Dredging | Norfolk, VA | 18500000 | 18300000 | -200000 | 14 | 14 | 0 | 3 | 280000 | Bobby M. | Complete
Conanicut Island Marina | Dredging | Jamestown, RI | 2400000 | 2380000 | -20000 | 3 | 3 | 0 | 1 | 55000 | Sarah K. | Complete
Sandwich Town Marine Maint | Dredging | Sandwich, MA | 3900000 | 4050000 | 150000 | 4 | 5 | 1 | 2 | 165000 | Bobby M. | Complete
Quincy Shipyard Wharf Recap | Pile Driving | Quincy, MA | 7800000 | 7900000 | 100000 | 7 | 8 | 1 | 2 | 145000 | Mike R. | Complete
Galveston Wharf Rehabilitation | Pile Driving | Galveston, TX | 4200000 | 4320000 | 120000 | 5 | 6 | 1 | 3 | 180000 | Mike R. | Complete
Cape Cod Canal Fender System | Pile Driving | Bourne, MA | 2900000 | 2870000 | -30000 | 4 | 4 | 0 | 1 | 45000 | Wes T. | Complete
Hyannis Ferry Terminal Recap | Pile Driving | Hyannis, MA | 5100000 | 5080000 | -20000 | 6 | 6 | 0 | 1 | 60000 | Mike R. | Complete
Throgs Neck Pier Reconstruction | Pile Driving | Bronx, NY | 9800000 | 10400000 | 600000 | 9 | 11 | 2 | 4 | 680000 | Wes T. | Complete
Salem Wharf Strengthening | Pile Driving | Salem, MA | 3300000 | 3280000 | -20000 | 4 | 4 | 0 | 0 | 0 | Mike R. | Complete
New London Sub Base Pier | Pile Driving | New London, CT | 14500000 | 14900000 | 400000 | 12 | 13 | 1 | 3 | 520000 | Wes T. | Complete
Cohasset Town Pier Replacement | Pile Driving | Cohasset, MA | 1900000 | 1950000 | 50000 | 3 | 3 | 0 | 1 | 42000 | Mike R. | Complete
Pawtucket WWTP Mechanical Upgrade | IPC Lydon | Pawtucket, RI | 8200000 | 9100000 | 900000 | 10 | 13 | 3 | 6 | 860000 | Peter S. | Complete
Holyoke Cogen Boiler Retrofit | IPC Lydon | Holyoke, MA | 6400000 | 7900000 | 1500000 | 8 | 12 | 4 | 9 | 1350000 | Peter S. | Complete
Chelsea Pump Station Mechanical | IPC Lydon | Chelsea, MA | 4800000 | 5100000 | 300000 | 6 | 7 | 1 | 4 | 280000 | Karen H. | Complete
Stoughton Process Piping Install | IPC Lydon | Stoughton, MA | 2900000 | 2960000 | 60000 | 4 | 5 | 1 | 2 | 75000 | Karen H. | Complete
Salem Steam Plant Repipe | IPC Lydon | Salem, MA | 5400000 | 6200000 | 800000 | 7 | 9 | 2 | 5 | 720000 | Peter S. | Complete
Gardner Power Plant Boiler Tube | IPC Lydon | Gardner, MA | 3700000 | 3650000 | -50000 | 5 | 5 | 0 | 1 | 55000 | Karen H. | Complete
Worcester Hospital Mech Phase 2 | IPC Lydon | Worcester, MA | 11800000 | 13400000 | 1600000 | 12 | 16 | 4 | 8 | 1450000 | Peter S. | Complete
Topeka Industrial Steam (Kansas) | IPC Lydon | Topeka, KS | 18500000 | 22900000 | 4400000 | 14 | 19 | 5 | 12 | 3900000 | Peter S. | Complete
Tampa LNG Storage Tank Phase 1 | Preload Cryogenics | Tampa, FL | 42000000 | 41500000 | -500000 | 22 | 22 | 0 | 2 | 380000 | Wes T. | Complete
Quintana Island LNG Tank Foundation | Preload Cryogenics | Quintana, TX | 38500000 | 47200000 | 8700000 | 20 | 27 | 7 | 11 | 7400000 | Wes T. | Complete
Sabine Pass LNG Tank Recap | Preload Cryogenics | Sabine Pass, LA | 61000000 | 75500000 | 14500000 | 28 | 34 | 6 | 14 | 12900000 | Karen H. | Complete
Cove Point LNG Tank Modifications | Preload Cryogenics | Lusby, MD | 29400000 | 31200000 | 1800000 | 18 | 20 | 2 | 6 | 1500000 | Wes T. | Complete
Freeport LNG Storage Tank #4 | Preload Cryogenics | Freeport, TX | 54000000 | 53800000 | -200000 | 24 | 24 | 0 | 3 | 600000 | Karen H. | Complete
Elba Island LNG Tank Refurb | Preload Cryogenics | Elba Island, GA | 19200000 | 23500000 | 4300000 | 14 | 18 | 4 | 9 | 3800000 | Wes T. | Complete
Plaquemines Parish LNG Tank Found | Preload Cryogenics | Plaquemines, LA | 45000000 | 51400000 | 6400000 | 22 | 27 | 5 | 10 | 5500000 | Karen H. | Complete
Calcasieu Pass LNG Phase 3 | Preload Cryogenics | Cameron, LA | 72000000 | 89500000 | 17500000 | 30 | 38 | 8 | 16 | 15200000 | Wes T. | In Progress
Notes
• All project names, regions, and figures in this workbook are HYPOTHETICAL and exist for AI-training purposes only.
• Cost Variance = Final Cost − Contract Value (positive = over budget)
• Schedule Variance = Actual Duration − Planned Duration (positive = late)
• Status "In Progress" rows have a Final Cost that's the latest forecast, not actual